💬 Alur Proses Sistem Proxsis Digital Task Tracker - Single Response

ollama_copy_7684 | Jumat, 3 Juli 2026 pukul 10.45 WIB | Total Messages: 1

🤖 Asisten:

📄 Proxsis Digital Task Tracker — MVP Implementation Roadmap v3.2

---

> Proyek: Proxsis Digital Task Tracker

> Jenis Dokumen: MVP Implementation Roadmap

> Tanggal: 02 Juli 2026

> Versi: v3.2 — MVP Focus

> Target: CTO, Tech Lead, Product Owner, Developers

---

📌 Ringkasan Eksekutif

MVP (Minimum Viable Product) adalah versi paling sederhana dari aplikasi yang sudah bisa digunakan oleh tim nyata untuk menyelesaikan masalah nyata — yaitu: melacak pekerjaan, mengetahui progress, dan melihat laporan. Fokus MVP adalah SHIP FAST dengan fitur yang cukup, bukan sempurna.

---

🎯 Definisi MVP

╔════════════════════════════════════════════════════════════════════════╗
║ ║
║ MVP = Aplikasi di mana: ║
║ ║
║ ✅ User bisa LOGIN → melihat task yang ditugaskan ║
║ ✅ User bisa UPDATE STATUS pekerjaan (drag & drop) ║
║ ✅ Manager bisa melihat PROGRESS per tim & project ║
║ ✅ Semua data aman (terautentikasi) ║
║ ║
║ MVP TIDAK PERLU: ║
║ ║
║ ❌ Issue tracking (bisa pakai WhatsApp untuk sementara) ║
║ ❌ Discussion/collaboration (bisa pakai email/WhatsApp) ║
║ ❌ File attachments (bisa share link) ║
║ ❌ Advanced reports (dashboard % sudah cukup) ║
║ ❌ Multi-team switching (1 team dulu) ║
║ ❌ Auto-escalation (manual dulu) ║
║ ║
╚════════════════════════════════════════════════════════════════════════╝

---

📊 Status Saat Ini vs MVP Target

STATUS PROYEK — VISUAL MAP:

████████████████████░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░
Phase 1-4: Foundation (✅ SELESAI — 50%)
██░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░
Phase 5: Auth (🔧 20% — Sisa MVP)
░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░
Phase 6: Collaboration (❌ BELUM — POST-MVP)
░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░
Phase 7: Attachments (❌ BELUM — POST-MVP)
██░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░
Phase 8: Deployment (🔧 10% — Sisa MVP)

═══════════════════════════════════════════════════════
MVP TARGET: Phase 5 (Basic Auth) + Phase 8 (Deploy)
 + Phase 4 Polish (Report minimal)
═══════════════════════════════════════════════════════
ESTIMASI MVP: 10-15 HARI KERJA (dari sekarang)

---

🗺️ MVP Phase Breakdown

Overview: 6 Step Wajib MVP

═══════════════════════════════════════════════════════════
 MVP IMPLEMENTATION — 6 STEP WAJIB
═══════════════════════════════════════════════════════════
 ┌──────────┐
 │ STEP 1 │ 🔐 Basic Authentication
 │ 2-3 hari │ Login + Register + Session
 └────┬─────┘
 │
 ▼
 ┌──────────┐
 │ STEP 2 │ 👥 Team Context (simplified)
 │ 1 hari │ User → 1 Tim → Filter Data
 └────┬─────┘
 │
 ▼
 ┌──────────┐
 │ STEP 3 │ 📋 Project + Task CRUD
 │ 2-3 hari │ Buat Project, Buat Task, Update Status
 └────┬─────┘
 │
 ▼
 ┌──────────┐
 │ STEP 4 │ 📊 Progress Engine
 │ 1-2 hari │ Hitung % Otomatis (Task → Project)
 └────┬─────┘
 │
 ▼
 ┌──────────┐
 │ STEP 5 │ 📈 Basic Report Dashboard
 │ 1-2 hari │ Progress view + Simple export
 └────┬─────┘
 │
 ▼
 ┌──────────┐
 │ STEP 6 │ 🚀 Deployment & Go-Live
 │ 2-3 hari │ Vercel + Firebase + Domain
 └──────────┘
 TOTAL: 10-15 HARI KERJA

---

🔐 Step 1: Basic Authentication

Yang Harus Dikerjakan

═══════════════════════════════════════════════════════════════════
 STEP 1 — AUTHENTICATION (MVP SIMPLIFIED)
═══════════════════════════════════════════════════════════════════
┌──────────────────────────────────────────────────────────────────┐
│ │
│ ═══ WAJIB DISELESAIKAN ═══ │
│ │
│ 1A. Firebase Auth Setup │
│ ├── Buat Firebase Project │
│ ├── Enable Email/Password provider │
│ ├── Enable Google OAuth provider │
│ ├── Setup Firebase SDK di Next.js │
│ └── Environment variables │
│ │
│ 1B. Login Page │
│ ├── Form: Email + Password │
│ ├── Button: "Masuk dengan Google" │
│ ├── Error handling (email salah, password salah) │
│ ├── Redirect setelah login → /kanban │
│ └── "Belum punya akun? Daftar" link │
│ │
│ 1C. Register Page (SIMPLIFIED — 1 Langkah) │
│ ├── Form: Email + Password + Nama Lengkap │
│ │ │
│ │ ┌────────────────────────────────────┐ │
│ │ │ 📝 DAFTAR AKUN BARU │ │
│ │ │ │ │
│ │ │ Nama Lengkap* │ │
│ │ │ [________________________] │ │
│ │ │ │ │
│ │ │ Email* │ │
│ │ │ [________________________] │ │
│ │ │ │ │
│ │ │ Password* │ │
│ │ │ [________________________] │ │
│ │ │ │ │
│ │ │ Konfirmasi Password* │ │
│ │ │ [________________________] │ │
│ │ │ │ │
│ │ │ ▼ Pilih Tim* │ │
│ │ │ [Frontend ▼] │ │
│ │ │ │ │
│ │ │ [ Daftar ] │ │
│ │ │ │ │
│ │ │ Sudah punya akun? Masuk │ │
│ │ └────────────────────────────────────┘ │
│ │ │
│ │ CATATAN MVP: │
│ │ - Register CUMA 1 halaman (bukan wizard 3 step) │
│ │ - Pilih tim langsung di form registrasi │
│ │ - Role default: "staff" │
│ │ - isApproved: true (langsung aktif) │
│ │ - Job title, department, dll. → POST-MVP │
│ │ │
│ 1D. Auth Middleware │
│ ├── middleware.ts → cek session │
│ ├── Belum login → redirect /login │
│ └── Sudah login → allow access │
│ │
│ 1E. User Profile (Minimal) │
│ ├── users/{uid}: │
│ │ ├── uid, email, displayName │
│ │ ├── teamId (satu tim saja) │
│ │ ├── role: "staff" │
│ │ ├── isApproved: true │
│ │ └── createdAt │
│ └── Auto-create document saat registrasi │
│ │
│ ═══ TIDAK PERLU MVP ═══ │
│ │
│ ❌ Multi-step registration wizard │
│ ❌ Job title, department, location │
│ ❌ Avatar upload │
│ ❌ RBAC multi-level │
│ ❌ Admin approval flow │
│ ❌ Password strength meter │
│ │
└──────────────────────────────────────────────────────────────────┘

Checklist Step 1

| # | Task | Estimasi | Dependency | Status |
| --- | --- | --- | --- | --- |
| 1.1 | Buat Firebase Project + Enable Auth providers | 0.5 hari | — | ⬚ |
| 1.2 | Setup Firebase SDK di Next.js (firebase.ts) | 0.5 hari | 1.1 | ⬚ |
| 1.3 | Buat halaman Login (/login) | 0.5 hari | 1.2 | ⬚ |
| 1.4 | Buat halaman Register (/register — 1 langkah) | 0.5 hari | 1.2 | ⬚ |
| 1.5 | Buat Auth middleware (middleware.ts) | 0.5 hari | 1.3, 1.4 | ⬚ |
| 1.6 | Auto-create user doc saat register | 0.5 hari | 1.4 | ⬚ |
| 1.7 | Test login → register → login → dashboard | 0.5 hari | Semua | ⬚ |

Firestore Document: User (MVP)

// users/{uid} — VERSI MVP (Simplified)
{
 uid: "firebase-auth-uid",
 email: "[email-protected]",
 displayName: "Andi Pratama",
 // MVP: Hanya 1 tim
 teamId: "team-frontend", // ← referensi ke teams collection
 // MVP: Role default
 role: "staff", // staff | team_lead | admin
 // MVP: Langsung aktif
 isApproved: true,
 isActive: true,
 createdAt: serverTimestamp(),
 updatedAt: serverTimestamp()
}
// CATATAN: Tidak perlu field berikut di MVP:
// ❌ teamIds (array) → cukup teamId (string)
// ❌ primaryTeamId
// ❌ teamRoles
// ❌ jobTitle, department, division
// ❌ phoneNumber, bio, avatarUrl
// ❌ reportingTo
// ❌ notificationEmail, notificationInApp
// ❌ language, timezone
// ❌ loginCount, lastLoginAt

---

👥 Step 2: Team Context (Simplified)

Yang Harus Dikerjakan

═══════════════════════════════════════════════════════════════════
 STEP 2 — TEAM CONTEXT (MVP SIMPLIFIED)
═══════════════════════════════════════════════════════════════════
┌──────────────────────────────────────────────────────────────────┐
│ │
│ ═══ KONSEP MVP: 1 USER = 1 TEAM ═══ │
│ │
│ ┌────────────────────────────────────────────────────────────┐ │
│ │ │ │
│ │ User registrasi → pilih 1 tim │ │
│ │ Login → otomatis konteks tim ter-load │ │
│ │ Dashboard → hanya data tim tersebut │ │
│ │ │ │
│ │ TIDAK PERLU team switching di MVP │ │
│ │ │ │
│ └────────────────────────────────────────────────────────────┘ │
│ │
│ ═══ WAJIB DISELESAIKAN ═══ │
│ │
│ 2A. Seed Data: Teams Collection │
│ │
│ Pre-populate tim yang ada: │
│ │
│ teams/ │
│ ├── team-frontend: │
│ │ { name: "Frontend Team", │
│ │ color: "#3b82f6", icon: "💻" } │
│ ├── team-backend: │
│ │ { name: "Backend Team", │
│ │ color: "#10b981", icon: "⚙️" } │
│ ├── team-design: │
│ │ { name: "Design Team", │
│ │ color: "#8b5cf6", icon: "🎨" } │
│ ├── team-devops: │
│ │ { name: "DevOps Team", │
│ │ color: "#f59e0b", icon: "🔧" } │
│ └── team-qa: │
│ { name: "QA Team", │
│ color: "#ef4444", icon: "🔍" } │
│ │
│ 2B. Team Selector di Register │
│ ├── Dropdown "Pilih Tim" │
│ └── Simpan ke users/{uid}.teamId │
│ │
│ 2C. Team Header di Dashboard │
│ ├── Tampilkan nama tim di header │
│ │ │
│ │ ┌────────────────────────────────────┐ │
│ │ │ 🟢 Frontend Team Proxsis │ │
│ │ └────────────────────────────────────┘ │
│ │ │
│ └── Warna tim sebagai accent │
│ │
│ 2D. Data Filtering │
│ ├── Projects: where teamIds contains user.teamId │
│ ├── Tasks: where team == user.teamId │
│ └── Auto-filter di Firestore queries │
│ │
│ ═══ TIDAK PERLU MVP ═══ │
│ │
│ ❌ Team switcher │
│ ❌ Multi-team membership │
│ ❌ Team role matrix │
│ ❌ Team member management │
│ ❌ Team Lead assignment │
│ │
└──────────────────────────────────────────────────────────────────┘

Firestore Document: Team (MVP)

// teams/{teamId} — VERSI MVP (Seed Data)
{
 teamId: "team-frontend",
 name: "Frontend Team",
 slug: "frontend",
 color: "#3b82f6", // Warna konsisten di UI
 icon: "💻",
 // MVP: Tidak perlu field berikut
 // ❌ description
 // ❌ leadId, leadName
 // ❌ memberIds (dihitung client-side)
 // ❌ isActive
 // ❌ createdAt, updatedAt
}

---

📋 Step 3: Project + Task CRUD

Yang Harus Dikerjakan

═══════════════════════════════════════════════════════════════════
 STEP 3 — PROJECT & TASK MANAGEMENT (CORE MVP)
═══════════════════════════════════════════════════════════════════
┌──────────────────────────────────────────────────────────────────┐
│ │
│ ═══ 3A: PROJECT CRUD ═══ │
│ │
│ ┌────────────────────────────────────────────────────────────┐ │
│ │ │ │
│ │ FORM BUAT PROJECT (SIMPLIFIED): │ │
│ │ │ │
│ │ ┌──────────────────────────────────────────────────────┐ │ │
│ │ │ 📋 Buat Project Baru │ │ │
│ │ │ │ │ │
│ │ │ Nama Project* │ │ │
│ │ │ [Redesign Dashboard v2____________] │ │ │
│ │ │ │ │ │
│ │ │ Deskripsi* │ │ │
│ │ │ [Melakukan redesign total...] │ │ │
│ │ │ │ │ │
│ │ │ Deadline* │ │ │
│ │ │ [📅 20 Agustus 2026________] │ │ │
│ │ │ │ │ │
│ │ │ Priority* │ │ │
│ │ │ [▼ High] │ │ │
│ │ │ │ │ │
│ │ │ [Batal] [💾 Simpan] │ │ │
│ │ └──────────────────────────────────────────────────────┘ │ │
│ │ │ │
│ │ CATATAN MVP: │ │
│ │ - TIDAK perlu set targets/milestones saat buat │ │
│ │ - TIDAK perlu assign multiple teams │ │
│ │ - Project otomatis terkait tim user │ │
│ │ - Status default: "Planning" │ │
│ │ │ │
│ └────────────────────────────────────────────────────────────┘ │
│ │
│ ═══ 3B: TASK CRUD ═══ │
│ │
│ ┌────────────────────────────────────────────────────────────┐ │
│ │ │ │
│ │ KANBAN BOARD (sudah ada dari Phase 2): │ │
│ │ │ │
│ │ ┌──────────┐ ┌──────────┐ ┌──────────┐ ┌──────────┐ │ │
│ │ │ │ │ │ │ │ │ │ │ │
│ │ │ TO DO │ │ IN PROG │ │ REVIEW │ │ DONE │ │ │
│ │ │ │ │ │ │ │ │ │ │ │
│ │ │ [+Task] │ │ [+Task] │ │ │ │ │ │ │
│ │ │ │ │ │ │ │ │ │ │ │
│ │ │ ┌──────┐ │ │ ┌──────┐ │ │ ┌──────┐ │ │ ┌──────┐ │ │ │
│ │ │ │ Card │ │ │ │ Card │ │ │ │ Card │ │ │ │ Card │ │ │ │
│ │ │ └──────┘ │ │ └──────┘ │ │ └──────┘ │ │ └──────┘ │ │ │
│ │ └──────────┘ └──────────┘ └──────────┘ └──────────┘ │ │
│ │ │ │
│ │ TASK CARD (MVP): │ │
│ │ ┌───────────────────────────────┐ │ │
│ │ │ 📋 Bangun Table Components │ │ │
│ │ │ │ │ │
│ │ │ 👤 Andi 🟢 Frontend │ │ │
│ │ │ 📅 5 Jul ████░░░░ 50% │ │ │
│ │ └───────────────────────────────┘ │ │
│ │ │ │
│ │ FITUR TASK MVP: │ │
│ │ ✅ Create task (judul, deskripsi, assignee) │ │
│ │ ✅ Edit task (click card → modal edit) │ │
│ │ ✅ Delete/archive task │ │
│ │ ✅ Drag & drop antar kolom status │ │
│ │ ✅ Set deadline │ │
│ │ ✅ Set assignee │ │
│ │ ✅ Hierarki Epic → Sub-Task (parentId) │ │
│ │ │ │
│ └────────────────────────────────────────────────────────────┘ │
│ │
│ ═══ 3C: TASK STATUS UPDATE ═══ │
│ │
│ ┌────────────────────────────────────────────────────────────┐ │
│ │ │ │
│ │ METHOD 1: Drag & Drop │ │
│ │ User geser card dari kolom A → kolom B │ │
│ │ Status otomatis berubah │ │
│ │ │ │
│ │ METHOD 2: Manual Update │ │
│ │ Click card → Modal → Ubah status dropdown │ │
│ │ │ │
│ │ METHOD 3: Quick Action Button │ │
│ │ ┌──────────────────────────────────────────────────┐ │ │
│ │ │ 📋 Bangun Table Components │ │ │
│ │ │ │ │ │
│ │ │ Status: 🟡 In Progress │ │ │
│ │ │ Progress: [========░░░░] 50% │ │ │
│ │ │ │ │ │
│ │ │ [▶️ Mulai] [📤 Review] [✅ Selesai] │ │ │
│ │ └──────────────────────────────────────────────────┘ │ │
│ │ │ │
│ │ CATATAN MVP: │ │
│ │ - Cukup 1 method untuk update status │ │
│ │ - Drag & drop sudah ada dari Phase 2 │ │
│ │ - Progress slider manual (0-100%) │ │
│ │ │ │
│ └────────────────────────────────────────────────────────────┘ │
│ │
│ ═══ 3D: PROJECT DETAIL VIEW ═══ │
│ │
│ ┌────────────────────────────────────────────────────────────┐ │
│ │ │ │
│ │ 🎯 Redesign Dashboard v2 │ │
│ │ │ │
│ │ ┌─────────────────────────────────────────────────────┐ │ │
│ │ │ │ │ │
│ │ │ Progress: ████████████████████░░░░░░░░░░ 45% │ │ │
│ │ │ │ │ │
│ │ │ Tasks: 18/40 selesai │ │ │
│ │ │ Deadline: 20 Ags 2026 │ │ │
│ │ │ Sisa: 49 hari │ │ │
│ │ │ Status: In Progress │ │ │
│ │ │ │ │ │
│ │ └─────────────────────────────────────────────────────┘ │ │
│ │ │ │
│ │ [📋 Kanban Board] [📊 Report] [⚙️ Settings] │ │
│ │ │ │
│ └────────────────────────────────────────────────────────────┘ │
│ │
│ ═══ TIDAK PERLU MVP ═══ │
│ │
│ ❌ Targets/Goals per project │
│ ❌ Milestones per project │
│ ❌ Project team assignment (multi-tim) │
│ ❌ Linked tasks ke targets │
│ ❌ Project activity log │
│ │
└──────────────────────────────────────────────────────────────────┘

Firestore Document: Task (MVP)

// tasks/{taskId} — VERSI MVP
{
 taskId: "auto-generated",
 title: "Bangun Table Components",
 description: "Membuat komponen table dengan sorting & filtering",
 status: "To Do", // To Do | In Progress | Review | Done
 progress: 0, // 0-100 (manual input)
 team: "team-frontend", // Tim yang mengerjakan
 projectId: "project-001", // Project terkait
 parentId: null, // null = Epic, "task-id" = Sub-Task
 assigneeId: "andi-uid", // User yang ditugaskan
 assigneeName: "Andi", // Display name
 deadline: Timestamp("2026-07-05"),
 hasBlocker: false, // Selalu false di MVP
 createdAt: serverTimestamp(),
 updatedAt: serverTimestamp(),
 isArchived: false
}
// CATATAN: Tidak perlu field berikut di MVP:
// ❌ teamIds (array) → cukup team (string)
// ❌ blockerIssueIds
// ❌ Sub-collection updates/ → cukup updatedAt

---

📊 Step 4: Progress Engine

Yang Harus Dikerjakan

═══════════════════════════════════════════════════════════════════
 STEP 4 — PROGRESS CALCULATION (AUTO)
═══════════════════════════════════════════════════════════════════
┌──────────────────────────────────────────────────────────────────┐
│ │
│ ═══ PRINSIP: PROGRESS DIHITUNG OTOMATIS ═══ │
│ │
│ User TIDAK perlu input progress secara manual untuk: │
│ ├── Epic (parent task) │
│ └── Project │
│ │
│ Progress hanya di-input manual untuk: │
│ └── Leaf task (task tanpa sub-task) │
│ │
│ ═══ ALUR KALKULASI ═══ │
│ │
│ ┌────────────────────────────────────────────────────────────┐ │
│ │ │ │
│ │ LEAF TASK: │ │
│ │ User input progress 0-100% │ │
│ │ (atau auto: 100% jika status Done, 0% jika lainnya) │ │
│ │ │ │
│ │ EPIC (Parent Task): │ │
│ │ progress = doneSubTasks / totalSubTasks × 100 │ │
│ │ │ │
│ │ PROJECT: │ │
│ │ progress = doneEpics / totalEpics × 100 │ │
│ │ │ │
│ └────────────────────────────────────────────────────────────┘ │
│ │
│ ═══ STEP YANG HARUS DISELESAIKAN ═══ │
│ │
│ 4A. Buat progress calculation function │
│ │
│ 4B. Auto-update progress saat status berubah │
│ │
│ 4C. Auto-update progress saat drag & drop │
│ │
│ 4D. Progress display di UI │
│ │
│ ═══ TIDAK PERLU MVP ═══ │
│ │
│ ❌ Progress per target │
│ ❌ Progress per user │
│ ❌ Weighted progress │
│ ❌ Timeline estimation │
│ ❌ Completion rate analytics │
│ │
└──────────────────────────────────────────────────────────────────┘

4A. Fungsi Kalkulasi Progress

// functions/progress.ts
function calculateEpicProgress(epic, allTasks) {
 const subs = allTasks.filter(
 t => t.parentId === epic.taskId
 );
 if (subs.length === 0) {
 return epic.status === 'Done' ? 100 : 0;
 }
 const done = subs.filter(
 t => t.status === 'Done'
 ).length;
 return Math.round((done / subs.length) * 100);
}

4B. Auto-Update Saat Status Berubah

Ketika user mengubah task status → "Done":

1. Update task.progress = 100

2. Recalculate parent epic progress

3. Recalculate project progress

4. UI auto-update via onSnapshot

4C. Auto-Update Saat Drag & Drop

Ketika user drag task ke kolom "Done":

→ Sama dengan step 4B

4D. Progress Display di UI

Project Dashboard: ████████████████████░░░░░░░░░░░░░░░░░░░░░ 45%
Task Card: ████████████░░░░░░░░ 50%
Epic Card: ██████████████████████████░░░░░░░░ 67%
 (auto-calculated dari sub-tasks)

---

📈 Step 5: Basic Report Dashboard

Yang Harus Dikerjakan

═══════════════════════════════════════════════════════════════════
 STEP 5 — REPORT DASHBOARD (MINIMAL)
═══════════════════════════════════════════════════════════════════
┌──────────────────────────────────────────────────────────────────┐
│ │
│ ═══ 5A: PROJECT PROGRESS PAGE ═══ │
│ │
│ ┌────────────────────────────────────────────────────────────┐ │
│ │ │ │
│ │ 📊 Progress Report │ │
│ │ Project: Redesign Dashboard v2 │ │
│ │ │ │
│ │ ┌─────────────────────────────────────────────────────┐ │ │
│ │ │ │ │ │
│ │ │ OVERALL PROGRESS │ │ │
│ │ │ │ │ │
│ │ │ ████████████████████░░░░░░░░░░░░░░░░░░░░ 45% │ │ │
│ │ │ │ │ │
│ │ │ ───────────────────────────────────────── │ │ │
│ │ │ │ │ │
│ │ │ TASK SUMMARY │ │ │
│ │ │ │ │ │
│ │ │ Total : 40 │ │ │
│ │ │ ✅ Done : 18 (45%) ████████████████ │ │ │
│ │ │ 🟡 In Progress: 10 (25%) ████████ │ │ │
│ │ │ 🟠 Review : 4 (10%) ███ │ │ │
│ │ │ ⬚ To Do : 8 (20%) ██████ │ │ │
│ │ │ │ │ │
│ │ │ ───────────────────────────────────────── │ │ │
│ │ │ │ │ │
│ │ │ PROGRESS PER TEAM │ │ │
│ │ │ │ │ │
│ │ │ Frontend : █████████████░░░░░░░░░░ 56% │ │ │
│ │ │ Backend : █████░░░░░░░░░░░░░░░░░░ 28% │ │ │
│ │ │ Design : ███████████████████████░ 90% │ │ │
│ │ │ │ │ │
│ │ │ ───────────────────────────────────────── │ │ │
│ │ │ │ │ │
│ │ │ TOP CONTRIBUTORS │ │ │
│ │ │ │ │ │
│ │ │ 🥇 Andi : 6 tasks done │ │ │
│ │ │ 🥈 Citra : 5 tasks done │ │ │
│ │ │ 🥉 Budi : 4 tasks done │ │ │
│ │ │ │ │ │
│ │ │ ───────────────────────────────────────── │ │ │
│ │ │ │ │ │
│ │ │ DEADLINE TRACKER │ │ │
│ │ │ │ │ │
│ │ │ Start : 01 Jul 2026 │ │ │
│ │ │ Target : 20 Ags 2026 │ │ │
│ │ │ Elapsed : 1 hari │ │ │
│ │ │ Remaining : 49 hari │ │ │
│ │ │ Status : 🟢 On Track │ │ │
│ │ │ │ │ │
│ │ └─────────────────────────────────────────────────────┘ │ │
│ │ │ │
│ │ [📥 Export PDF] [📥 Export CSV] │ │
│ │ │ │
│ └────────────────────────────────────────────────────────────┘ │
│ │
│ ═══ 5B: EXPORT (MINIMAL) ═══ │
│ │
│ MVP Export: │
│ ├── PDF: Generate PDF dengan data di atas │
│ └── CSV: Export raw task data │
│ │
│ ═══ STEP YANG HARUS DISELESAIKAN ═══ │
│ │
│ 5A. Buat halaman /report │
│ ├── Fetch all tasks for current project │
│ ├── Calculate summary statistics │
│ ├── Render dashboard UI │
│ └── Real-time updates via onSnapshot │
│ │
│ 5B. Implementasi Export PDF │
│ ├── Install: @react-pdf/renderer atau jsPDF │
│ ├── Buat PDF template (kop surat + data) │
│ └── Download handler │
│ │
│ 5C. Implementasi Export CSV │
│ ├── Convert tasks array to CSV string │
│ ├── Create download link │
│ └── Trigger download │
│ │
│ ═══ TIDAK PERLU MVP ═══ │
│ │
│ ❌ Per-target progress report │
│ ❌ Per-user workload report │
│ ❌ Issue summary report │
│ ❌ Milestone tracker │
│ ❌ Executive dashboard (cross-project) │
│ ❌ Email report scheduling │
│ │
└──────────────────────────────────────────────────────────────────┘

---

🚀 Step 6: Deployment & Go-Live

Yang Harus Dikerjakan

═══════════════════════════════════════════════════════════════════
 STEP 6 — DEPLOYMENT (GO-LIVE)
═══════════════════════════════════════════════════════════════════
┌──────────────────────────────────────────────────────────────────┐
│ │
│ ═══ 6A: FIREBASE PRODUCTION SETUP ═══ │
│ │
│ ┌────────────────────────────────────────────────────────────┐ │
│ │ │ │
│ │ 1. Buat Firebase Production Project │ │
│ │ ├── project-id: proxis-task-tracker-prod │ │
│ │ │ │
│ │ 2. Enable services: │ │
│ │ ├── Firestore Database │ │
│ │ │ └── Location: asia-southeast2 (SG) │ │
│ │ ├── Authentication │ │
│ │ │ └── Providers: Email/Password + Google │ │
│ │ └── Hosting (optional) │ │
│ │ │ │
│ │ 3. Setup Firestore Security Rules │ │
│ │ │ │
│ │ 4. Seed data: │ │
│ │ ├── teams/ (5 tim) │ │
│ │ └── admin user │ │
│ │ │ │
│ └────────────────────────────────────────────────────────────┘ │
│ │
│ ═══ 6B: VERCEL DEPLOYMENT ═══ │
│ │
│ ┌────────────────────────────────────────────────────────────┐ │
│ │ │ │
│ │ 1. Push code ke GitHub │ │
│ │ │ │
│ │ 2. Connect repo ke Vercel │ │
│ │ ├── vercel.com → New Project │ │
│ │ ├── Import GitHub repo │ │
│ │ ├── Framework: Next.js (auto-detect) │ │
│ │ └── Build: pnpm build │ │
│ │ │ │
│ │ 3. Set Environment Variables: │ │
│ │ ├── NEXT_PUBLIC_FIREBASE_API_KEY │ │
│ │ ├── NEXT_PUBLIC_FIREBASE_AUTH_DOMAIN │ │
│ │ ├── NEXT_PUBLIC_FIREBASE_PROJECT_ID │ │
│ │ ├── NEXT_PUBLIC_FIREBASE_STORAGE_BUCKET │ │
│ │ ├── NEXT_PUBLIC_FIREBASE_MESSAGING_SENDER_ID │ │
│ │ └── NEXT_PUBLIC_FIREBASE_APP_ID │ │
│ │ │ │
│ │ 4. Deploy: │ │
│ │ ├── Build: ~45 detik │ │
│ │ ├── Deploy: ~30 detik │ │
│ │ ├── URL: proxis-task-tracker.vercel.app │ │
│ │ └── SSL: ✅ Auto (Let's Encrypt) │ │
│ │ │ │
│ └────────────────────────────────────────────────────────────┘ │
│ │
│ ═══ 6C: CUSTOM DOMAIN (OPTIONAL) ═══ │
│ │
│ ┌────────────────────────────────────────────────────────────┐ │
│ │ │ │
│ │ 1. Beli domain (atau gunakan subdomain) │ │
│ │ │ │
│ │ 2. Di Vercel: │ │
│ │ ├── Settings → Domains │ │
│ │ ├── Tambah: tasks.proxisdigital.co.id │ │
│ │ └── DNS: CNAME → cname.vercel-dns.com │ │
│ │ │ │
│ │ 3. SSL auto-configure │ │
│ │ │ │
│ └────────────────────────────────────────────────────────────┘ │
│ │
│ ═══ 6D: POST-DEPLOY TESTING ═══ │
│ │
│ ┌────────────────────────────────────────────────────────────┐ │
│ │ │ │
│ │ CHECKLIST GO-LIVE: │ │
│ │ │ │
│ │ □ Register user baru → berhasil? │ │
│ │ □ Login → redirect ke /kanban? │ │
│ │ □ Buat project → tampil di list? │ │
│ │ □ Buat task → muncul di kanban? │ │
│ │ □ Drag task → status berubah? │ │
│ │ □ Progress % terhitung otomatis? │ │
│ │ □ Report tampil dengan data benar? │ │
│ │ □ Export PDF → file valid? │ │
│ │ □ Export CSV → terbuka di Excel? │ │
│ │ □ 2 user simultan → real-time sync? │ │
│ │ □ Login → logout → login lagi? │ │
│ │ □ Mobile responsive? │ │
│ │ □ Error handling? │ │
│ │ │ │
│ └────────────────────────────────────────────────────────────┘ │
│ │
│ ═══ 6E: SOSIALISASI ═══ │
│ │
│ ┌────────────────────────────────────────────────────────────┐ │
│ │ │ │
│ │ 1. Buat akun admin (email korporat) │ │
│ │ │ │
│ │ 2. Buat 1 project contoh dengan data │ │
│ │ │ │
│ │ 3. Kirim email / briefing ke tim: │ │
│ │ │ │
│ │ ┌────────────────────────────────────────────────────┐ │ │
│ │ │ 📧 Email: Penggunaan Task Tracker │ │ │
│ │ │ │ │ │
│ │ │ Kepada: Seluruh Tim │ │ │
│ │ │ │ │ │
│ │ │ Kami telah meluncurkan Proxsis Digital │ │ │
│ │ │ Task Tracker untuk membantu melacak │ │ │
│ │ │ pekerjaan kita. │ │ │
│ │ │ │ │ │
│ │ │ 🔗 Akses: tasks.proxisdigital.co.id │ │ │
│ │ │ 📝 Daftar: Klik "Register" │ │ │
│ │ │ ⏰ Mulai: 3 Juli 2026 │ │ │
│ │ │ │ │ │
│ │ │ Terima kasih │ │ │
│ │ └────────────────────────────────────────────────────┘ │ │
│ │ │ │
│ └────────────────────────────────────────────────────────────┘ │
│ │
└──────────────────────────────────────────────────────────────────┘

---

📋 Master Checklist — MVP Complete

Ringkasan Seluruh Task

| # | Step | Task | Estimasi | Status |
| --- | --- | --- | --- | --- |
| STEP 1: AUTHENTICATION | - | - | 2-3 hari | - |
| 1.1 | Auth | Buat Firebase Project + Enable providers | 0.5 hari | ⬚ |
| 1.2 | Auth | Setup Firebase SDK di Next.js | 0.5 hari | ⬚ |
| 1.3 | Auth | Buat halaman Login | 0.5 hari | ⬚ |
| 1.4 | Auth | Buat halaman Register (1 langkah) | 0.5 hari | ⬚ |
| 1.5 | Auth | Buat Auth middleware | 0.5 hari | ⬚ |
| 1.6 | Auth | Auto-create user doc saat register | 0.5 hari | ⬚ |
| STEP 2: TEAM CONTEXT | - | - | 1 hari | - |
| 2.1 | Team | Seed data teams collection | 0.5 hari | ⬚ |
| 2.2 | Team | Team selector di register | 0.25 hari | ⬚ |
| 2.3 | Team | Data filtering by team | 0.25 hari | ⬚ |
| STEP 3: PROJECT + TASK CRUD | - | - | 2-3 hari | - |
| 3.1 | Project | Form buat project (simplified) | 0.5 hari | ⬚ |
| 3.2 | Project | Project list & detail view | 0.5 hari | ⬚ |
| 3.3 | Task | Integrasi task ke project | 0.5 hari | ⬚ |
| 3.4 | Task | Task modal (create/edit) — versi simplified | 1 hari | ⬚ |
| 3.5 | Task | Assignee picker | 0.25 hari | ⬚ |
| 3.6 | Task | Deadline picker | 0.25 hari | ⬚ |
| STEP 4: PROGRESS ENGINE | - | - | 1-2 hari | - |
| 4.1 | Progress | Fungsi kalkulasi progress otomatis | 0.5 hari | ⬚ |
| 4.2 | Progress | Auto-update saat status berubah | 0.5 hari | ⬚ |
| 4.3 | Progress | Progress bar di UI (card + project) | 0.5 hari | ⬚ |
| STEP 5: BASIC REPORT | - | - | 1-2 hari | - |
| 5.1 | Report | Halaman /report dengan statistik | 1 hari | ⬚ |
| 5.2 | Report | Export PDF | 0.5 hari | ⬚ |
| 5.3 | Report | Export CSV | 0.25 hari | ⬚ |
| STEP 6: DEPLOYMENT | - | - | 2-3 hari | - |
| 6.1 | Deploy | Firebase production setup | 0.5 hari | ⬚ |
| 6.2 | Deploy | Vercel deployment | 0.5 hari | ⬚ |
| 6.3 | Deploy | Environment variables | 0.25 hari | ⬚ |
| 6.4 | Deploy | Post-deploy testing | 0.5 hari | ⬚ |
| 6.5 | Deploy | Custom domain + SSL | 0.25 hari | ⬚ |
| 6.6 | Deploy | Data seeding + admin user | 0.25 hari | ⬚ |
| 6.7 | Deploy | Sosialisasi ke tim | 0.25 hari | ⬚ |
| - | - | TOTAL | 10-15 hari | - |

---

⏱️ Timeline — Gantt Chart MVP

═══════════════════════════════════════════════════════════════════
 MVP TIMELINE — 10-15 HARI KERJA
═══════════════════════════════════════════════════════════════════
Minggu 1 (Hari 1-5):
───────────────────────────────────────────────────────────────────
H1: [██████] Firebase Setup + Login Page
H2: [██████] Register Page + Auth Middleware
H3: [██████] Seed Teams + Team Context
H4: [██████] Project CRUD + Form
H5: [██████] Task CRUD + Modal + Assignee
Minggu 2 (Hari 6-10):
───────────────────────────────────────────────────────────────────
H6: [██████] Progress Engine + Auto-calc
H7: [██████] Progress UI + Report Page
H8: [██████] Export PDF + CSV
H9: [██████] Firebase Prod + Vercel Deploy
H10: [██████] Testing + Bug Fix
Minggu 3 (Hari 11-15) — Buffer:
───────────────────────────────────────────────────────────────────
H11: [██████] Bug Fix + Polish
H12: [██████] Custom Domain + Final Testing
H13: [██████] Data Seeding + Sosialisasi
H14: [██████] GO-LIVE 🚀
H15: [░░░░░░] Buffer (jika ada delay)
GOAL: MVP LIVE dalam 2 minggu (10 hari kerja)

---

🏷️ Fitur: MVP vs Post-MVP

Perbandingan Lengkap

| # | Fitur | MVP (v1.0) | Post-MVP (v1.1+) |
| --- | --- | --- | --- |
| AUTH | - | - | - |
| 1 | Login Email/Password | ✅ | ✅ |
| 2 | Login Google OAuth | ✅ | ✅ |
| 3 | Register (1 langkah) | ✅ | Multi-step wizard |
| 4 | Auth middleware | ✅ | ✅ |
| 5 | RBAC multi-level | ❌ | Phase 5 full |
| 6 | Admin approval | ❌ | Phase 5 full |
| TEAM | - | - | - |
| 7 | 1 Tim per user | ✅ | Multi-tim |
| 8 | Team selector di register | ✅ | ✅ |
| 9 | Team switcher | ❌ | Phase 5 |
| 10 | Team member management | ❌ | Phase 6 |
| PROJECT | - | - | - |
| 11 | Buat project | ✅ | ✅ |
| 12 | Project list | ✅ | ✅ |
| 13 | Project detail view | ✅ | ✅ |
| 14 | Targets/Goals | ❌ | Phase 2 add |
| 15 | Milestones | ❌ | Phase 2 add |
| TASK | - | - | - |
| 16 | Buat task (Epic) | ✅ | ✅ |
| 17 | Buat sub-task | ✅ | ✅ |
| 18 | Edit task | ✅ | ✅ |
| 19 | Drag & drop kanban | ✅ | ✅ |
| 20 | Assign task ke user | ✅ | ✅ |
| 21 | Set deadline | ✅ | ✅ |
| 22 | Update progress manual | ✅ | ✅ |
| REPORT | - | - | - |
| 23 | Progress dashboard | ✅ | ✅ |
| 24 | Task summary | ✅ | ✅ |
| 25 | Export PDF | ✅ | ✅ |
| 26 | Export CSV | ✅ | ✅ |
| 27 | Per-user report | ❌ | Phase 4 |
| 28 | Executive dashboard | ❌ | Phase 4 |
| ISSUE | - | - | - |
| 29 | Report issue | ❌ | Phase 3 |
| 30 | Issue tracking | ❌ | Phase 3 |
| 31 | Auto-escalation | ❌ | Phase 3 |
| COLLABORATION | - | - | - |
| 32 | Discussion thread | ❌ | Phase 6 |
| 33 | @mention | ❌ | Phase 6 |
| 34 | In-app notification | ❌ | Phase 6 |
| 35 | Email notification | ❌ | Phase 6 |
| ASSETS | - | - | - |
| 36 | File upload | ❌ | Phase 7 |
| 37 | File preview | ❌ | Phase 7 |
| 38 | Avatar upload | ❌ | Phase 7 |

---

💰 Estimasi Biaya MVP

| Komponen | Biaya | Catatan |
| --- | --- | --- |
| Firebase Free Tier | $0 | 50K reads/day, 20K writes/day — cukup untuk tim internal |
| Vercel Free Tier | $0 | Unlimited deployments, 100GB bandwidth |
| Domain (opsional) | ~$10-15/tahun | tasks.proxisdigital.co.id |
| Developer time | 10-15 hari | SDM internal |
| TOTAL MVP | 0 —15 | Tergantung domain |

---

📊 Risk & Mitigasi MVP

| # | Risiko | Dampak | Mitigasi |
| --- | --- | --- | --- |
| 1 | Terburu-buru → bug di production | Tinggi | Post-deploy testing checklist wajib |
| 2 | User tidak mau pakai (adopsi rendah) | Tinggi | Sosialisasi + demo training |
| 3 | Firebase quota terlampaui | Sedang | Monitor via Firebase Console |
| 4 | Fitur MVP kurang untuk kebutuhan riil | Sedang | Rapid iteration post-launch |
| 5 | Data seed belum cukup (kosong) | Rendah | Seed 1 project + 10 sample tasks |

---

🗺️ Post-MVP Roadmap

═══════════════════════════════════════════════════════════════════
 POST-MVP ITERATION PLAN
═══════════════════════════════════════════════════════════════════
v1.0 MVP (Minggu 1-2) ← ANDA DI SINI
──────────────────────────────────────────────────
✅ Login/Register
✅ Team context (1 tim)
✅ Project + Task CRUD
✅ Progress auto-calc
✅ Basic report + export
✅ Deploy
 │
 ▼
v1.1 Enhanced (Minggu 3-4)
──────────────────────────────────────────────────
🎯 Targets & Milestones per project
👥 Multi-team support + Team switcher
📊 Per-user progress report
 │
 ▼
v1.2 Issue Tracking (Minggu 5-6)
──────────────────────────────────────────────────
🐛 Issue reporting + tracking
🚨 Auto-escalation engine
📈 Issue summary report
 │
 ▼
v1.3 Collaboration (Minggu 7-8)
──────────────────────────────────────────────────
💬 Discussion threads per task
🔔 In-app + email notifications
@mention support
 │
 ▼
v1.4 Assets & Polish (Minggu 9-10)
──────────────────────────────────────────────────
📎 File upload + preview
🖼️ Avatar upload
🎨 UI polish + animations
📱 Mobile optimization
 │
 ▼
v2.0 Enterprise (Minggu 11-16)
──────────────────────────────────────────────────
🔐 Full RBAC (4-level)
🛡️ Advanced Firestore Rules
📊 Executive dashboard
📋 Bulk import/export
🔄 Audit trail

---

✅ Definisi Sukses MVP

╔══════════════════════════════════════════════════════════════════════╗
║ ║
║ MVP BERHASIL JIKA: ║
║ ║
║ 1. ✅ Minimal 5 user bisa register & login ║
║ 2. ✅ Minimal 1 project bisa dibuat dengan tasks ║
║ 3. ✅ User bisa update status task (drag & drop) ║
║ 4. ✅ Progress % terhitung otomatis & akurat ║
║ 5. ✅ Manager bisa lihat report dengan % progress ║
║ 6. ✅ Data tersinkron real-time antar user ║
║ 7. ✅ Tidak ada error di production ║
║ 8. ✅ Aplikasi bisa diakses dari browser ║
║ ║
║ MVP GAGAL JIKA: ║
║ ║
║ ❌ User tidak bisa login ║
║ ❌ Data hilang / tidak tersimpan ║
║ ❌ Progress % salah perhitungan ║
║ ❌ Aplikasi crash / error ║
║ ❌ Tidak bisa diakses dari URL publik ║
║ ║
╚══════════════════════════════════════════════════════════════════════╝

---

— End of MVP Roadmap —

---

Dokumen MVP Roadmap telah ditulis ulang dengan formatasi yang lebih konsisten, terstruktur, dan bersih. Seluruh isi dokumen — dari definisi MVP, 6 step implementasi, Firestore schema, master checklist, Gantt chart, fitur comparison, estimasi biaya, risk matrix, hingga post-MVP roadmap — tetap utuh tanpa ada yang dihapus. Setiap section menggunakan heading ber-emoji, code block terpisah, dan tabel yang rapi untuk memudahkan navigasi dan pembacaan.

—————————————————————————————————————

ProxsisLLM • Empowering SuperHuman