## Ringkasan Status
Dokumentasi Progress Kerja — Task Tracker App
Project | Task Tracker App
Repository | Task_Tracker_App
Update Terakhir | 9 Juli 2026
Environment | Next.js 16 + React 19 + Prisma 7 + PostgreSQL
Mode Catatan | Progress implementasi / changelog kerja
Ringkasan Status Pekerjaan
Area | Status | Keterangan Singkat
Database PostgreSQL & Prisma | ✅ Selesai | Schema, migration, client, model baru sudah berjalan
Authentication & Session | ✅ Selesai | Login/logout/session/AuthGuard stabil
Department System | ✅ Selesai | Operational, Marketing, Management
Settings / Users / Profile | ✅ Selesai | Role & Permission UI, user management, profile
Form Marketing | ✅ Selesai | Single input, multiple input, draft, batch submit
Detail Lead Page | ✅ Selesai | Search, filter, pagination, detail per lead
Marketing Dashboard | ✅ Selesai | Summary, chart, ranking, tabel + pagination
Deadline & Notification | ✅ Selesai | dueDate, overdue checker, bell notification
Integrasi Odoo | ⚠️ Belum selesai | Masih bridge stub

## Log Progress
Log Progress Pekerjaan Detail
Area | Task | Status | Progress (Kegiatan) | File Terkait | Next Step
3.1 Database & Prisma | Menyiapkan database PostgreSQL dan struktur data aplikasi. | ✅ Selesai | - Setup PostgreSQL local (App_Tracker) - Setup Prisma ORM - Generate Prisma client - Singleton Prisma client di src/lib/prisma.ts - Model dasar: User, Task, Project, Milestone, Notification, AuditLog - Auth fields di User - Model LeadSource + audit trail - Enum Department + field departments di User - Model LeadEntry + field typeOfNeed - Migration dibuat dan diaplikasikan | prisma/schema.prisma prisma/migrations/** src/lib/prisma.ts | Tidak ada blocker
3.2 Authentication & Session | Membuat sistem login, logout, dan proteksi route. | ✅ Selesai | - Login via /api/auth/login - Logout via /api/auth/logout - Current user via /api/auth/me - Session cookie berbasis token - AuthGuard untuk proteksi halaman - Perbaikan error 404 auth route - Patch hydration warning di halaman login | src/app/api/auth/login/route.ts src/app/api/auth/logout/route.ts src/app/api/auth/me/route.ts src/features/tasks/store/authStore.ts src/app/login/page.tsx src/features/tasks/components/AuthGuard.tsx | Tidak ada blocker
3.3 Department System | Menambahkan department-based access dan dashboard per department. | ✅ Selesai | - Department awal: MARKETING, OPERATIONAL - Ditambahkan MANAGEMENT - Department switcher di header - Current department disimpan di localStorage - Default department logic diperbaiki - Mapping akses halaman per department di AuthGuard - Navbar menyesuaikan department aktif - Management dibatasi ke akses Board - ManagementDashboard dengan toggle Task Board & Marketing Data | src/features/tasks/types/user.ts src/features/tasks/store/authStore.ts src/features/tasks/components/DepartmentSwitcher.tsx src/features/tasks/components/AppHeader.tsx src/features/tasks/components/AuthGuard.tsx src/features/tasks/components/ManagementDashboard.tsx src/app/page.tsx | Jika diperlukan, Management bisa dibatasi lebih ketat menjadi full view only
3.4 Settings / Users / Profile | Menyediakan halaman pengaturan, user management, profile, dan hak akses. | ✅ Selesai | #NAME? | src/app/settings/page.tsx src/app/users/page.tsx src/app/profile/page.tsx src/app/api/users/route.ts src/app/api/users/[id]/route.ts src/app/api/users/me/route.ts src/app/api/users/me/name/route.ts src/app/api/users/me/password/route.ts | Persistence permission role ke database (saat ini masih local browser)
3.5 Form Marketing / Lead Source | Membuat sistem form marketing: input summary, detail lead, draft, detail view. | ✅ Selesai | - Halaman /lead-sources - Section periode report, tanggal & bulan otomatis - Reset form setelah save - Riwayat: tabel history (25/page), search, Details, Hapus - Single Input: 1 form + channel picker → submit ke DB - Multiple Input: card per channel, draft lokal (save/edit/hapus), batch submit - Lead Entry: model + endpoint, summary otomatis update count | src/app/lead-sources/page.tsx src/app/api/lead-sources/route.ts src/app/api/lead-sources/[id]/route.ts src/app/api/lead-entries/route.ts prisma/schema.prisma | Klik detail dari card summary/dashboard lain jika dibutuhkan
3.6 Halaman Detail Lead Source | Membuat halaman detail untuk melihat isi lead per channel dan per entry. | ✅ Selesai | - Halaman /lead-sources/[id] - Tombol Back to Lead Form - Detail: title, month, period, total leads - Tabs filter per channel, search, filter need type - Pagination 25 data/halaman - Detail per lead: Name, Phone, Email, Company, Position, Need Type, Source Info, Diinput Oleh | src/app/lead-sources/[id]/page.tsx src/app/api/lead-sources/[id]/route.ts | Tidak ada blocker
3.7 Marketing Dashboard | Membuat dashboard marketing: summary, chart, ranking, tabel data. | ✅ Selesai | - MarketingDashboard component - Summary: Total Entri, Total Leads, Top Channel, Periode Terakhir - Detail input periode terakhir + comparison - Ranking channel - Tabel semua data form (25/page) - Charts: line chart, doughnut chart - Periode 1 hari tampil 1 tanggal | src/features/tasks/components/MarketingDashboard.tsx | Dashboard bisa ditambah link klik ke detail tertentu
3.8 Task Board, Deadline & Notification | Membuat task board dengan dukungan deadline dan notifikasi. | ✅ Selesai | - Task board / kanban - Field dueDate di task - Endpoint cek overdue task - Bell notification di header - Mark as read / mark all as read - Polling notifikasi setiap 30 detik | src/features/tasks/components/TaskBoard.tsx src/features/tasks/components/AppHeader.tsx src/app/api/notifications/route.ts src/app/api/notifications/[id]/route.ts src/app/api/notifications/read-all/route.ts src/app/api/notifications/check-deadlines/route.ts | Tidak ada blocker
3.9 Integrasi Odoo | Menyiapkan bridge integrasi ke Odoo. | ⚠️ Belum selesai | - Struktur bridge service dibuat - Fungsi stub: test connection, sync task, delete task, fetch stages - Belum ada koneksi nyata ke server Odoo | src/features/integrations/services/odooService.ts | Koneksi real ke Odoo API Sinkronisasi session/auth Mapping stage real Persistence hasil sync

## Bugfix & Perbaikan
Bugfix & Perbaikan Teknis
UI / UX
Item | Keterangan
Reset form | Tidak kembali ke sample values lagi
Refresh halaman form | Tidak memunculkan sample default lagi
Periode 1 hari | Tampil sebagai 1 tanggal
History table | Dipagination
Dashboard table | Dipagination
Details page | Dipagination
Hydration warning login | Dipatch
State / Logic
Item | Keterangan
Auth route 404 | Teratasi setelah regenerate + restart dev server
ThemeContext lint error | set-state-in-effect dibersihkan
AppHeader notification flow | set-state-in-effect dibersihkan
Profile page state | Dirapikan
Multiple input draft | Sekarang bisa save, edit, hapus, submit batch
Data Dummy
Item | Keterangan
Riwayat data tersimpan | >25 data
Detail lead source | >25 leads
Multi-channel lead entries | Sesuai format form terbaru

## File & Quality
File Penting & Quality Check
File Baru Penting
File | Keterangan
ARCHITECTURE.md | Arsitektur project
Docs/dokumentasi.md | Dokumentasi ini
src/features/tasks/components/ManagementDashboard.tsx | Dashboard Management
src/app/profile/page.tsx | Halaman profile
src/app/settings/page.tsx | Halaman settings
src/app/api/users/me/route.ts | API user me
src/app/api/users/me/name/route.ts | API update nama
src/app/api/users/me/password/route.ts | API update password
src/app/api/lead-entries/route.ts | API lead entries
src/app/lead-sources/[id]/page.tsx | Halaman detail lead
File Utama yang Banyak Berubah
File | Keterangan
prisma/schema.prisma | Schema database
src/app/lead-sources/page.tsx | Halaman lead sources
src/app/api/lead-sources/route.ts | API lead sources
src/app/api/lead-sources/[id]/route.ts | API detail lead
src/features/tasks/components/AppHeader.tsx | Header app
src/features/tasks/components/AuthGuard.tsx | Auth guard
src/features/tasks/components/MarketingDashboard.tsx | Dashboard marketing
src/features/tasks/store/authStore.ts | Auth store
src/features/tasks/types/user.ts | User types
Quality Check
Command | Status | Keterangan
npx tsc --noEmit | ✅ Aman | TypeScript compile tanpa error
npm run lint | ✅ Tanpa error | Masih ada warning kecil lama di beberapa file
Warning yang Masih Tersisa
File | Status | Keterangan
src/app/api/users/me/route.ts | Warning kecil
src/app/users/page.tsx | Warning kecil
src/features/integrations/services/odooService.ts | Warning kecil

## Backlog
Backlog / Yang Masih Kurang
No | Item | Keterangan
1 | Integrasi Odoo real | Koneksi ke Odoo API + sinkronisasi
2 | Report marketing final | Sesuai kebutuhan bisnis
3 | Management full view only | Jika ingin dibatasi lebih ketat
4 | Navigation dari summary | Semua angka summary/dashboard bisa diklik ke detail
5 | Sinkronisasi role permission ke database | Saat ini masih local browser
Ringkasan Siap Update Odoo
Kategori | Item | Status
Sudah selesai | Database PostgreSQL | ✅
Sudah selesai | Sistem Form | ✅
Sudah selesai | Visualisasi Dashboard | ✅
Sudah selesai | Sistem Deadline | ✅
Belum selesai | Integrasi Odoo | ⚠️
Catatan Penting
No | Fitur | Keterangan
1 | Single input | Form lead 1 per channel
2 | Multiple input | Card per channel, batch submit
3 | Draft system | Simpan draft lokal sebelum submit
4 | Batch submit | Kirim semua draft ke DB sekaligus
5 | Details page | Lihat detail per lead
6 | Pagination | 25 data per halaman
7 | Search/filter | Filter channel, need type
8 | Lead detail per channel | Detail input per lead